## Proposed Product Backlog
Category | User Stories (Epics) | Assigned To
User | <As a> User, <I want to> open the app <so that> I can see the login page. | Jacob
<As a> User, <I want to> create an account <so that> I can access the app.
<As a> User, <I want to> log in to my account <so that> I can view my home screen.
<As a> User, <I want to> see my homescreen display my account stats <so that> I can track account progress.
<As a> User, <I want to> open a drawer on the home screen <so that> I can view my profile, friends, card collection, decks, cards recommended to me, or the store.
<As a> User, <I want to> open the store to get additional cards <so that> I can add them to my collection.
<As a> User, <I want to> view my friends list <so that> I can see my friends and add or delete them.
<As a> User, <I want to> select friends in my friends list and compare stats <so that> I can gloat about my wins.
<As a> User, <I want to> view my profile <so that> I can make changes to it.
<As a> User, <I want to> view my card collection <so that> I may sort my cards and browse through them.
<As a> User, <I want to> view my decks <so that> I may add, delete or edit them.
<As a> User, <I want to> view cards recommended to me <so that> I can see what my friends suggest I use and swipe through them.
Admin | <As a> Admin, <I want to> log in to my account <so that> I may access my admin abilities.
<As a> Admin, <I want to> see the homescreen display what actions I may take <so that> I can navigate my options immediately.
<As a> Admin, <I want to> view a list of registered accounts <so that> I may add, delete or edit them.
<As a> Admin, <I want to> view cards in the database <so that> I can make changes.
<As a> Admin, <I want to> create and add cards to the database <so that> I can document card ideas on the go.

## Sprint1
Sprint Backlog: Sprint 1
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
User | <As a> User, <I want to> open the app <so that> I can see the login page. | 1 | <As a> User, <I want to> see the title of the app displayed <so that> I know I'm using the right app. | Jacob | in progress
|  | 2 | <As a> User, <I want to> see login screen organized <so that> everything looks nice. |  | completed
| <As a> User, <I want to> create an account <so that> I can access the app. | 3 | <As a> User, <I want to> pick a username for myself <so that> can share it with friends. |  | in progress
|  | 4 | <As a> User, <I want to> hit a button to create my account <so that> I can login to the app. |  | completed
| <As a> User, <I want to> log in to my account <so that> I can view my home screen. | 5 | <As a> User, <I want to> login using my email and password <so that> no one else can sign into my account. |  | completed
|  | 6 | <As a> User, <I want to> login into the app quickly <so that> I don't have to wait around while it loads. |  | completed
| <As a> User, <I want to> see my homescreen display my account stats <so that> I can track account progress. | 7 | <As a> User, <I want to> see my account stats <so that> I know what I have accomplished. |  | in progress
|  | 8 | <As a> User, <I want to> see my cards displayed below my stats <so that> I can quickly scroll through them. |  | completed
| <As a> User, <I want to> open a drawer on the home screen <so that> I can view my profile, friends, card collection, decks, cards recommended to me, or the store. | 9 | <As a> User, <I want to> open a drawer <so that> I can see my profile info and navigational options. |  | completed
completed

## Sprint1 Acceptance
Child User Story ID | Acceptance Criteria | created by (member) | verified by (test engineer) | tested by (test engineer) | Result | Note
1 | The title should be centered horizontally. | Jacob |  |  | pass
| The title should fade in on application start. |  |  |  | fail | The fade-in works, but it happens before the screen becomes visible.
| The title's capital letters should be a fontSize of 36. |  |  |  | pass
| The title's lowercase letters should be a fontSize of 13. |  |  |  | pass
2 | The title should be the top-most object (other than the appBar) |  |  |  | pass
| The login form should be below the title. |  |  |  | pass
| The login form should have a white background to distinguish it. |  |  |  | pass
3 | The display name should at least 4 characters long. |  |  |  | pass
| The display name should be unique. |  |  |  | fail
4 | Account creation should take less than 5 seconds. |  |  |  | pass
| Upon successful creation a popup will notify the user. |  |  |  | pass
| Upon unsuccessful creation a popup will notify the user. |  |  |  | pass
| Firestore stores the user's account in the user collection. |  |  |  | pass
5 | The email must match the email the user registered with. |  |  |  | pass
| The password must match the password the user registered with |  |  |  | pass
| Firestore validates the provided info against the database. |  |  |  | pass
6 | Logging in should take less than 5 seconds. |  |  |  | pass
| Logging in should notify the user if there is a problem. |  |  |  | pass
7 | Account stats should be up-to-date. |  |  |  | fail | No implemetation for storing account stats yet.
| Account stats should be easily readable. |  |  |  | pass
8 | If there a more cards than can be displayed, the view should be scrollable. |  |  |  | pass
| The cards should be laid out in a grid. |  |  |  | pass
| The cards should have a 5px margin on all sides. |  |  |  | pass
| The cards should display the name of the card and it's image. |  |  |  | pass
9 | The drawer should open within 5 seconds. |  |  |  | pass
| The basic user info should be displayed in the top-left corner of the drawer. |  |  |  | pass
| The drawer should show all possible pages to navigate to. |  |  |  | pass
| The drawer should also close when I navigate away. |  |  |  | pass

## Sprint2
Sprint Backlog: Sprint 1
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
User | <As a> User, <I want to> open the app <so that> I can see the login page. | 1 | <As a> User, <I want to> see the title of the app displayed <so that> I know I'm using the right app. | Jacob | in progress | fwd Sprint 3
| <As a> User, <I want to> view my friends list <so that> I can see my friends and add or delete them. | 2 | <As a> User, <I want to> view my friends list <so that> I can make changes to it. |  | completed
| <As a> User, <I want to> view my profile <so that> I can make changes to it. | 3 | <As a> User, <I want to> to view my profile info <so that> I can change my information. |  | completed
| <As a> User, <I want to> view cards recommended to me <so that> I can see what my friends suggest I use and swipe through them. | 4 | <As a> User, <I want to> see cards recommended<so that> can check them out. |  | completed
| <As a> User, <I want to> see my homescreen display my account stats <so that> I can track account progress. | 5 | <As a> User, <I want to> see my stats update <so that> I can track my progress. |  | completed

## Sprint2 Acceptance
Child User Story ID | Acceptance Criteria | created by (member) | verified by (test engineer) | tested by (test engineer) | Result | Note
1 | The title should be centered horizontally. | Jacob |  |  | pass
| The title should fade in on application start. |  |  |  | fail | The fade-in works, but it happens before the screen becomes visible.
| The title's capital letters should be a fontSize of 36. |  |  |  | pass
| The title's lowercase letters should be a fontSize of 13. |  |  |  | pass
2 | You can add any user by their displayName. |  |  |  | pass
| You can remove any user with a button. |  |  |  | pass
| You can't add the same user twice. |  |  |  | pass
| You can't add yourself as a friend. |  |  |  | pass
| If your friends list exceeds the view you can scroll through them. |  |  |  | pass
| When you press the add button your friendslist is updated in Firebase. |  |  |  | pass
3 | All profile information is displayed, except information controlled by the app. |  |  |  | pass
| All information can be changed, except email. |  |  |  | pass
| Current password must be entered to both fields to make any changes. |  |  |  | pass
| If you enter the same password in both fields, the account will update. |  |  |  | pass
| If you enter different passwords in both fields, the account will update including the new password. |  |  |  | pass
| When you press the update button all of the fields are updated in Firebase. |  |  |  | pass
4 | All cards shared with me are displayed in a page view. |  |  |  | pass
| Each card takes up 80% of the screen. |  |  |  | pass
| The card list is scrollable horizontally. |  |  |  | pass
| Each card lists all of its information from its creation. |  |  |  | pass
5 | All account stats are displayed with current information. |  |  |  | pass
| Number of friends is updated as friends are added. |  |  |  | pass
Number of cards is updated as cards are added.
Number of decks is updated as decks are added.
As each stat is updated in the app it also then updated in Firebase

## Sprint4
Sprint Backlog: Sprint 4
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
User | <As a> User, <I want to> open the store to get additional cards <so that> I can add them to my collection. | 1 | <As a> User, <I want to> purchase cards from the store <so that> I have more cards to use. | Jacob | completed
| <As a> User, <I want to> select friends in my friends list and compare stats <so that> I can gloat about my wins. | 2 | <As a> User, <I want to> compare stats with any friend <so that> I can compare progress. |  | completed
| <As a> User, <I want to> view my card collection <so that> I may sort my cards and browse through them. | 3 | <As a> User, <I want to> view all of my cards on the homepage <so that> I can search them or browse. |  | completed
| <As a> User, <I want to> view my decks <so that> I may add, delete or edit them. | 4 | <As a> User, <I want to> view all of my created decks <so that> I can make changes. |  | completed
Admin | <As a> Admin, <I want to> log in to my account <so that> I may access my admin abilities. | 5 | <As a> Admin, <I want to> login and be directed to the admin page <so that> I can do admin stuff. |  | completed
| <As a> Admin, <I want to> see the homescreen display what actions I may take <so that> I can navigate my options immediately. | 6 | <As a> Admin, <I want to> see my admin abilities <so that> I can make appropriate changes. |  | completed
| <As a> Admin, <I want to> view a list of registered accounts <so that> I may add, delete or edit them. | 7 | <As a> Admin, <I want to> view all registered accounts <so that> I may make changes. |  | completed
| <As a> Admin, <I want to> view cards in the database <so that> I can make changes. | 8 | <As a> Admin, <I want to> view all cards in the database <so that> I edit them. |  | completed
| <As a> Admin, <I want to> create and add cards to the database <so that> I can document card ideas on the go. | 9 | <As a> Admin, <I want to> be able to add new cards to the database <so that> I can document ideas. |  | completed

## Sprint4 Acceptance
Child User Story ID | Acceptance Criteria | created by (member) | verified by (test engineer) | tested by (test engineer) | Result | Note
1 | The store should display all cards in the database. | Jacob |  |  | all pass
When one of the cards is tapped it opens the CardView page.
When the user presses the buy button, the price is deducted from the user's points. Firestore is updated.
When the buy button is pressed, Firestore updates the user's account with the new card.
If the user already has the card, they are prevented from buying it again.
2 | When the user presses the compare button it opens the CompareFriendsPage.
The page displays all of the user's stats and the friend's stats side-by-side.
3 | All of the user's cards are displayed on the homepage.
The cards are searchable by name.
The user can browse and tap them for more information.
4 | All of the user's decks are displayed, with the top card being shown as the image.
Each deck has a name below it.
When a new deck is created, it is stored in Firebase.
When a deck is deleted, it is deleted from Firebase.
5 | Upon login the admin is routed to a different homepage with 2 buttons.
One button is the Registered Account button.
The other button is the Card Database button.
6 | When the Registered Accounts button is pressed, it opens the RegisteredAccountsPage
When the Card Database button is pressed, it opens the StorePage.
The admin can also open the drawer to sign out.
7 | All registered accounts are displayed in no particular order in a Listview builder.
Any account can be deleted from Firebase by clicking the Delete icon.
Any account can have its info updated by clicking the Edit icon.
When the edit icon is clicked it shows the ProfilePage with the clicked user's information.
Upon hitting save, the user's information is updated in Firebase.
8 | All available cards are shown.
Any card can be deleted from Firebase by a long-press followed by hitting the delete button.
Any card can be edited by tapping it.
Upon hitting save on a card, it is updated in Firebase.
9 | A card can be added by clicking on the floating action button.
After the card information is filled out and submitted it is updated in Firebase.

## Finalized Product Backlog
ALL Completed Child User Stories Based on the Submitted Program.
Category | Child User Stories | Assigned To | Status | Notes
User | <As a> User, <I want to> see login screen organized <so that> everything looks nice. | Jacob | all completed
<As a> User, <I want to> pick a username for myself <so that> can share it with friends.
<As a> User, <I want to> hit a button to create my account <so that> I can login to the app.
<As a> User, <I want to> login using my email and password <so that> no one else can sign into my account.
<As a> User, <I want to> login into the app quickly <so that> I don't have to wait around while it loads.
<As a> User, <I want to> see my account stats <so that> I know what I have accomplished.
<As a> User, <I want to> see my cards displayed below my stats <so that> I can quickly scroll through them.
<As a> User, <I want to> open a drawer <so that> I can see my profile info and navigational options.
<As a> User, <I want to> view my friends list <so that> I can make changes to it.
<As a> User, <I want to> to view my profile info <so that> I can change my information.
<As a> User, <I want to> see cards recommended<so that> can check them out.
<As a> User, <I want to> see my stats update <so that> I can track my progress.
<As a> User, <I want to> purchase cards from the store <so that> I have more cards to use.
<As a> User, <I want to> compare stats with any friend <so that> I can compare progress.
<As a> User, <I want to> view all of my cards on the homepage <so that> I can search them or browse.
<As a> User, <I want to> view all of my created decks <so that> I can make changes.
Admin | <As a> Admin, <I want to> login and be directed to the admin page <so that> I can do admin stuff.
<As a> Admin, <I want to> see my admin abilities <so that> I can make appropriate changes.
<As a> Admin, <I want to> view all registered accounts <so that> I may make changes.
<As a> Admin, <I want to> view all cards in the database <so that> I edit them.
<As a> Admin, <I want to> be able to add new cards to the database <so that> I can document ideas.